## Sprint Backlog
Sprint Backlog - Corporate Training System Project
Item | Story Points | Status | Estimate | Responsible
Sprint #1
Draw ERD |  | Done | 1 day | ThinhLP
Draw usecase diagram |  | Done | 1 day | ThinhLP
Design Mockup
- Manage User page |  | Done | 0.5 day | AnhDT
- Manage Plan page |  | Done | 1 day | ThinhLP
- Manage Course page |  | Done | 2 days | NguyenVT
- Manage Brand page |  | Done | 0.5 day | AnhDT
- Manage skill page |  | Done | 0.5 day | NguyenVT
- Learner plan page |  | Done | 1 day | NguyenVT
- Plan overview page |  | Done | 1 day | ThinhLP
- User profile page |  | Done | 1 day | HungPC
- Learning page - Video lecture, text lecture, slideshow |  | Done | 1 day | HungPC
- Learning page - Quiz lecture |  | Done | 1 day | HungPC
- Login page |  | Done | 0.5 day | AnhDT
Report 1
- Introduction, current situation |  | Done | 0.5 day | NguyenVT
- Problem definition |  | Done | 0.5 day | HungPC
- Proposed solution |  | Done | 0.5 day | Nguyen VT
- Functional requirement, role responsibility |  | Done | 0.5 day | HungPC
Sprint #2
Fix ERD |  | Done | 1 day | ThinhLP
Implement prototype
- Master page |  | Done | 1 day | ThinhLP
- Login page |  | In process | 0.5 day | AnhDT
- Manage Page
+ Manage user page |  | In process | 0.5 day | AnhDT
+ Manage brand page |  | In process | 1 day | HungPC
+ Manage course page
+ Manage skill page |  | In process | 1 day | HungPC
- Learner page
+ User plan page |  | Done | 1 day | ThinhLP
+ Plan overview page |  | In process | 2 days | ThinhLP
Report 2
+ Problem definition |  | Done | 0.5 day | HungPC
+ Project Organization |  | Done | 0.5 day | HungPC
+ Project Management |  | Done | 0.5 day | NguyenVT
+ Coding convention |  | Done | 0.5 day | NguyenVT
Sprint #3
Implement prototype
- Manage page
+ Finish manage course page |  | To do | 2 days | NguyenVT
+ Manage plan |  | To do | 3 days | ThinhLP
- Learner page
+ Learning page (Quiz) |  | To do | 2 days | HungPC
+ Learning page (Text / powerpoint / video) |  | To do | 1 days | NguyenVT
+ View quiz result page |  | To do | 1 days | HungPC
+ |  | To do