## Sheet1
Sprint Backlog - Corporate Training System Project
Item | Story Points | Responsible | Status | Estimate
Sprint #1
Draw ERD |  | ThinhLP | Done | 1 day
Draw usecase diagram |  | ThinhLP | Done | 1 day
Design Mockup
- Manage User page |  | AnhDT | Done | 0.5 day
- Manage Plan page |  | ThinhLP | Done | 1 day
- Manage Course page |  | NguyenVT | Done | 1.5 day
- Manage Brand page |  | AnhDT | Done | 0.5 day
- Manage skill page |  | NguyenVT | Done | 0.5 day
- Learner plan page |  | NguyenVT | Done | 1 day
- Plan overview page |  | ThinhLP | Done | 1 day
- User profile page |  | HungPC | Done | 1 day
- Learning page - Video lecture, text lecture, slideshow |  | HungPC | Done | 1 day
- Learning page - Quiz lecture |  | HungPC | Done | 1 day
- Login page |  | AnhDT | Done | 0.5 day
Report 1
- Introduction, current situation
- Problem definition
- Proposed solution
Sprint #2
Fix ERD |  | ThinhLP |  | 1 day
3
Task |  |  |  | 2
Task |  |  |  | 5
Sprint #3 | 5
Task |  |  |  | 8
Task |  |  |  | 3
Task |  |  |  | 1.5
Task |  |  |  | 2